## #10d Summary Tables
The summary tables below are categorized by island and interconnection voltage level. Interconnection requirements generally increase in complexity as voltage increases. The tables provide summary information for the Interconnection Requirements Studies (IRS) and interconnection work that have been completed to date; the "# of projects" column illustrates the number of projects included in each Summary. Many projects are still going through the development process, so these summary tables will be further populated and updated as project work is completed. For more detailed information on each project, please see the spreadsheet file provided in the Download Historical Data button below.
Cost to Interconnect Summary
| Voltage | Average IRS Cost per project, Actual | # of projects | Average Interconnection (Company-Owned Facilities) Cost per project, Actual | # of projects
Oahu | 12 KV | 181528.64 | 1 | 3345777.7 | 1
| 46 KV | 219769.5954 | 6 | 3400356.554 | 5
| 138 KV | 146958.3441 | 4 | 12067618.17 | 2
Maui | 12 KV | 37500 | 4 | 281201.34 | 3
| 69 KV | 111749.225 | 2
Hawaii | 12 KV
| 69 KV | 236795.06 | 1
Lanai | 12 KV
Molokai | 12 KV
Notes:
1. Cost summaries above reflect projects completed to date from 2017 through 2020 (pre-Stage 1 and Stage 2). Stage 1 and 2 projects will be added upon completion.
2. Costs reflect only the Company's portion of the Company-Owned Interconnection Facilities (COIF). Company's scope and cost will vary by project, depending on whether the COIF is Company- or Developer-built. Projects done in the past often included the Company building a larger portion of the COIF and therefore they likely have had higher costs, whereas for projects currently under construction, the COIF is primarily being designed, procured and constructed by the developers and once completed, this chart will likely reflect much smaller numbers for the Company-built portion. The Company is not provided information from the developers on the final cost of the COIF for the portions built by the developer.
3. IRS actual cost includes any additional work required to accommodate Developer equipment or design changes.
Time to Interconnect Summary
| Voltage | Average System Impact Study Duration per project (months), Actual Step 2 | # of projects | Average Facility Study Duration per project (months), Actual Step 2a + Step 3 | # of projects
Oahu | 12 KV
| 46 KV | 6 | 4 | 4.5 | 2
| 138 KV | 5 | 5 | 5.5 | 2
Maui | 12 KV
| 69 KV | 4.6 | 5 | 5 | 1
Hawaii | 12 KV
| 69 KV | 4 | 2
Lanai | 12 KV
Molokai | 12 KV
Notes:
1. Together, the System Impact Study (SIS) and the Facility Study (FS) comprise the IRS. The SIS assesses the performance and impact that the operation of the proposed project(s) have on the system. The FS takes into account the SIS findings and requirements and determines the estimated cost, scope, and schedule of the Company-Owned Interconnection Facilities that must be designed, procured and installed to interconnect the proposed Project and bring the proposed Project into Commercial Operations.
2. Time summaries above reflect only the SIS and FS, rather than the completed IRS, which includes Developer Acceptance (Step 4). The summaries also do not include the time required to obtain working models and model check-out (Steps 1 and 1a).
3. Projects completed in 2017 through 2020 are not included because they did not utilize the bifurcated IRS process.

## #10d Interconnection Costs
IPP Interconnection Reported Metric Cost to Interconnect
[8 empty] | Interconnection Requirements Study2 Advanced Payments |  |  |  |  | Interconnection Requirements Study2 Actual Costs |  |  | Company Costs for Company-Owned Interconnection Facility3
Project Name | Island | Technology | Size | Commercial Operations Date | Contract Type | Inter- connection Voltage | RFP Unit Cost 1 | System Impact Study (SIS) Deposit | Facility Study (FS) Deposit | SIS Additional Payments | FS Additional Payments | Total (I+J+K+L) | SIS Actual Cost, including PUC/PSC Taxes | FS Actual Cost, including PUC/PSC Taxes | Total (N+O) | Company or Developer Constructed4 | Estimated Interconnection Facility Costs5 | Actual Interconnection Facility Costs | Variance (R-S)
Waianae Solar | Oahu | PV | 27.6 MW | 2017-01-14 | RAP | 46 KV | N/A |  |  |  |  | 127000 | 108288.25 | 12938.3909 | 121226.6409 | Developer | 2185027 | 1694843.47 | 490183.53
Aloha Solar 15-01 | Oahu | PV | 5 MW | 2017-03-15 | As-Avail | 46 KV | N/A |  |  |  |  | 130000 | 108530.18 | 21694.7 | 130224.88 | Company | 2622666 | 2295002.44 | 327663.56
Lanikuhana Solar | Oahu | PV | 14.7 MW | 2019-09-19 | RAP | 138 KV | N/A |  |  |  |  | 86000 | 68800.8392 | 15618.3872 | 84419.2264 | Company | 13160941 | 12505792.36 | 655148.64
Waipio PV | Oahu | PV | 45.9 MW | 2019-09-19 | RAP | 138 KV | N/A |  |  |  |  | 146000 | 118168.43 | 17612.87 | 135781.3 | Company | 12789122 | 11629443.98 | 1159678.02
Kawailoa Solar | Oahu | PV | 49 MW | 2019-11-20 | RAP | 46 KV | N/A |  |  |  |  | 282000 | 268388.9567 | 27277.2347 | 295666.1914 | Company | 6094009 | 5630968.19 | 463040.81
Aloha Solar 15-02 | Oahu | PV | 5 MW | 2020-04-02 | As-Avail | 12 KV | N/A |  |  |  |  | 200000 | 146030.08 | 35498.56 | 181528.64 | Company | 3836912 | 3345777.7 | 491134.3
Mauka FIT 14-01 | Oahu | PV | 3.486 MW | 2020-10-13 | As-Avail | 46 KV | N/A |  |  |  |  | 205279.64 | 165758.49 | 37554.03 | 203312.52 | Company | 5484619 | 3222053.21 | 2262565.79
Na Pua Makani | Oahu | Wind | 24 MW | 2020-12-11 | As-Avail | 46 KV | N/A |  |  |  |  | 409799.99 | 359852.97 | 44574.27 | 404427.24 | Developer | 4990000 | 4158915.46 | 831084.54
Ho'ohana Solar 1, LLC | Oahu | PV + BESS | 52/208 MWh |  | RDG | 138 KV | N/A | 83000 | 60000 | 48880 |  | 191880 | TBD | 58246.52 | TBD | Developer | 4983676 | TBD
Mililani I Solar, LLC | Oahu | PV + BESS | 39 MW/156 MWh | 2022-07-31 | RDG | 138 KV | N/A | 96000 | 60000 | 26205 |  | 182205 | TBD | 50156.23 | TBD | Company | 2418880 | 1235915.15 | 1182964.85
AES West Oahu Solar, LLC | Oahu | PV + BESS | 12.5/50 MWh |  | RDG | 46 KV | N/A | 90000 | 60000 | 7553 |  | 157553 | 103589.37 | 60170.73 | 163760.1 | Developer | 2212004
Waiawa Solar Power LLC | Oahu | PV + BESS | 36 MW/144MWh | 2023-01-11 | RDG | 46 KV | N/A | 90000 | 60000 | 40591 |  | 190591 | TBD | 59224.95 | TBD | Developer | 3092286 | 2396464.3 | 695821.7
Kupehau Solar | Oahu | PV + BESS | 60MW/240MWh |  | RDG | 138 KV | N/A | 150000 | 70000 | 0 |  | 220000 | 118876.81 | 53728.62 | 172605.43 | Developer | See note 7
Mahi Solar, LLC | Oahu | PV + BESS | 120MW/480MWh |  | RDG | 138 KV | N/A | 150000 | 70000 | 30000 |  | 250000 | 131366.15 | 63661.27 | 195027.42 | Developer | See note 8
Mountain View Solar | Oahu | PV + BESS | 7MW/35MWh |  | RDG | 46 KV | N/A | 100000 | 70000 | 57000 |  | 227000 | TBD | TBD | TBD | Developer | TBD | TBD
Waiawa Phase 2 Solar | Oahu | PV + BESS | 30MW/240MWh |  | RDG | 46 KV | N/A | 100000 | 70000 | 75000 |  | 245000 | TBD | TBD | TBD | Developer | TBD | TBD
Kapolei Energy Storage | Oahu | BESS | 185 MW | 2023-12-19 | RDG | 138 KV | N/A | 150000 | 70000 | 57000 |  | 277000 | TBD | 69397.77 | TBD | Developer | 4642371 | TBD
South Maui Renewable Resources | Maui | PV | 2.87 MW | 2018-05-05 | RAP | 12 KV | N/A |  |  |  |  | 40000 | 40000 | See note 6 | 40000 | Company | 130000 | 243174.09 | -113174.09
Kuia Solar | Maui | PV | 2.87 MW | 2018-10-04 | RAP | 12 KV | N/A |  |  |  |  | 40000 | 40000 | See note 6 | 40000 | Company | 130000 | 266894.04 | -136894.04
Maui 17-2 | Maui | PV | 0.735 MW | 2020-03-31 | FIT As-Avail | 12 KV | N/A |  |  |  |  | 35000 | 35000 | See note 6 | 35000 | Company | 265312.94 | 333535.89 | -68222.95
Maui 17-1 LLC | Maui | PV | 1 MW |  | FIT As-Avail | 12 kV | N/A |  |  |  |  | 0 | 35000 | See note 6 | 35000 | Developer | TBD | TBD
AES Kuihelani | Maui | PV + BESS | 60 MW/240 MWh |  | RDG | 69 KV | N/A | 90000 | 60000 | 93914 |  | 243914 | 187790.94 | 35707.51 | 223498.45 | Developer/Company | 4928007 | TBD
Paeahu Solar LLC | Maui | PV + BESS | 15 MW/60 MWh |  | RDG | 69 KV | N/A | 90000 | 60000 | 115000 |  | 265000 | TBD | 61407.19 | TBD | Company | 1397000 | See note 12
Pulehu Solar | Maui | PV + BESS | 40MW/160MWh |  | RDG | 69 KV | N/A | 150000 | 70000 | 50000 |  | 270000 | 148075.46 | See note 9
Kahana Solar | Maui | PV + BESS | 20MW/80MWh |  | RDG | 69 KV | N/A | 90000 | 70000 | TBD |  | 160000 | TBD | 39822.17 | TBD | Developer | 2306585 | See note 10
Kamaole Solar | Maui | PV + BESS | 40MW/160MWh |  | RDG | 69 KV | N/A | 150000 | 70000 | TBD |  | 220000 | TBD | TBD | TBD | Developer | See note 11
AES Waikoloa Solar, LLC | Hawaii | PV + BESS | 30MW/120MWh | 2023-04-21 | RDG | 69 KV | N/A | 90000 | 60000 | 109669 |  | 259669 | 197891.26 | 38903.8 | 236795.06 | Developer | 1718191 | 2474070.5 | -755879.5
Hale Kuawehi Solar LLC | Hawaii | PV + BESS | 30MW/120 MWh |  | RDG | 69 KV | N/A | 90000 | 60000 | 140000 |  | 290000 | TBD | 44604.68 | TBD | Developer | 1930829 | TBD
Notes:
1 This RFP Unit Cost pertains to the Company's portion of the Company-Owned Interconnection Facilities (COIF). For the Stage 1 and Stage 2 projects, the RFP Unit Cost provided in Appendix H of the RFP were based on the scenario where the Company would build the COIF. However, in Stage 1, most of the projects selected developer-build and in Stage 2, projects were required to be developer-build so the costs in Appendix H may not be applicable to the Stage 1 and Stage 2 projects. See also Note 4 below.
2 The Interconnection Requirements Study (IRS) is comprised of a System Impact Study (SIS) and Facility Study (FS). For the Stage 1 and Stage 2 projects, the IRS payments were bifurcated into SIS and FS deposits.
3 As set forth in the Companies' Refined Proposal filed on March 16, 2021 in Docket 2018-0088, "For purposes of this Scorecard, the Companies have interpreted “cost to connect to the network” as the cost for Company-owned interconnection facilities paid for by the IPP, but developed by the utility" (page 26)
4 Even if the project selects Developer-build, a portion of the COIF work still remains with the Company. For Developer-build projects, the cost reflected in this spreadsheet is for the COIF work that remains with the Company. It does not reflect the cost incurred by the Developer to engineer, procure and construct the COIF as this information is not provided by the Developers to the Companies.
5 This number reflects the estimate in the executed IRS Amendment.
6Prior to consolidating the administration and negotiation of IPP projects on all islands to one division, Maui Electric did not separate the cost of the Facility Study from the System Impact Study. Starting with the Stage 1 RFP projects all IPP projects follow the same process reporting the System Impact Study and Facility Study separately.
7 Null and void as of Dec 6, 2021.
8 Null and void as of May 4, 2022. Costs are current until Null and Void declaration.
9 Null and void as of May 4, 2022. Costs are current until Null and Void declaration.
10 Null and void as of Dec 23, 2022. Costs are current until Null and Void declaration.
11 Null and void as of Mar 13, 2023. Costs are current until Null and Void declaration.
12 Null and void as of Nov 17, 2023. Costs are current until Null and Void declaration.

## #10d Interconnection Time
IPP Interconnection Reported Metric Time to Interconnect
Project Name | Island | Tech | Size | Commercial Operations Date | Inter-connection Voltage | Step 1 From Company Request to Receipt of IRS1 Data and Model4 Collection to Start System Impact Study (SIS) (Months) |  | Step 1a From Company Request of Developer Drawings to Completion of Company SLD's/Receipt of Developer Drawings (Months) |  | Step 2 Start of SIS to SIS Results (Months) |  | Step 2a Start of Preliminary FS to Preliminary FS Results (Months) |  | Step 3 Start of Final FS to Acceptance of Final FS (Months) |  | Step 4 Presentation of Final IRS Results to Acceptance by Developer (Months) |  | Step 4a Acceptance of IRS to Execution of IRS Amendment (Months) | Step 5 Execution of IRS Amendment to Filing of IRS Amendment and Line Approval (Months) | Step 6 File IRS Amendment to Receive Approval to Construct Line Extension (Months) | Step 7 Engineering/Design/ Procurement/Construction to Commercial Operations (Months) |  | Total (Steps 1-7) From Request of IRS Data to Commercial Operations3 (Months) | Total Time from PPA Execution to Commercial Operations (Months)
[6 empty] | Company | Developer | Company | Developer | Company | Developer | Company | Developer | Company | Developer | Company | Developer | Company/Developer2 | Company | Company/Developer/CA/PUC | Company | Developer
Waianae Solar | Oahu | PV | 27.6 MW | 2017-01-14 | 46 KV | [18 empty] | 25.9333
Aloha Solar 15-01 | Oahu | PV | 5 MW | 2017-03-15 | 46 KV | [18 empty] | 19.129
Lanikuhana Solar | Oahu | PV | 14.7 MW | 2019-09-19 | 138 KV | [18 empty] | 31.6129
Waipio PV | Oahu | PV | 45.9 MW | 2019-09-19 | 138 KV | [18 empty] | 31.6129
Kawailoa Solar | Oahu | PV | 49 MW | 2019-11-20 | 46 KV | [18 empty] | 31.0968
Aloha Solar 15-02 | Oahu | PV | 5 MW | 2020-04-02 | 12 KV | [18 empty] | 23.4516
Mauka FIT 14-01 | Oahu | PV | 3.5 MW | 2020-10-13 | 46 KV | [18 empty] | 31.5161
Na Pua Makani | Oahu | Wind | 24 MW | 2020-12-11 | 46 KV | [18 empty] | 84.7097
Ho'ohana Solar 1, LLC | Oahu | PV + BESS | 52 MW/208 MWh |  | 138 KV | 10 |  | N/A | N/A | 5 |  | N/A |  | N/A | N/A | 0 | 2 | 10 | 0 | 5 | TBD | TBD | TBD
Mililani I Solar, LLC | Oahu | PV + BESS | 39 MW/156 MWh | 2022-07-31 | 138 KV | 10 |  | N/A | N/A | 3 |  | N/A |  | N/A | N/A | 0 | 2 | 4 | 0.93548 | N/A | 26 | 26 | 46 | 44
AES West Oahu Solar, LLC | Oahu | PV + BESS | 12.5 MW/50 MWh |  | 46 KV | 5 |  | N/A | N/A | 5 |  | N/A |  | N/A | N/A | 0 | 0 | 6 | 0 | 6.1613 | TBD | TBD | TBD
Waiawa Solar Power LLC | Oahu | PV + BESS | 36 MW/144MWh | 2023-01-11 | 46 KV | 10 |  | N/A | N/A | 5 |  | N/A |  | N/A | N/A | 0 | 2 | 4 | 1.8065 | 5.1935 | 20 | 42 | 48 | 49
Kupehau Solar | Oahu | PV + BESS | 60 MW/240 MWh |  | 138 KV | 1 | 3 | 1 | 2 | 7 |  | 1 |  | 2 | See note 5
Mahi Solar, LLC | Oahu | PV + BESS | 120 MW/480 MWh |  | 138 KV | 1 | 6 | 5 | 4 | 6 |  | 1 |  | 2 | 1 | 0 | 1 | See note 6
Mountain View Solar | Oahu | PV + BESS | 7 MW/35 MWh |  | 46 KV | 2 | 4 | 1 | 6 | 7 |  | 1 |  | 1 | 3 | 0 | 1 | 6 | 6 | 5 | TBD | TBD | TBD
Waiawa Phase 2 Solar | Oahu | PV + BESS | 30 MW/240 MWh |  | 46 KV | 2 | 4 | 1 | 6 | 7 |  | 1 |  | 2 | 1 | 0 | 1 | 6 | 6 | 3 | TBD | TBD | TBD
Kapolei Energy Storage | Oahu | BESS | 185 MW | 2023-12-19 | 138 KV | 2 | 4 | 1 | 2 | 4 |  | 2 |  | 2 | 3 | 0 | 0 | 2 | 0 | 1 | 38 | 37 | 42 | 39
South Maui Renewable Resources | Maui | PV | 2.87 MW | 2018-05-05 | 12 KV | [18 empty] | 33.3548
Kuia Solar | Maui | PV | 2.87 MW | 2018-10-04 | 12 KV | [18 empty] | 38.2581
Maui 17-2 | Maui | PV | 0.735 MW | 2020-03-31 | 12 KV | [18 empty] | 25.4516
Maui 17-1 LLC | Maui | PV | 1 MW |  | 12 kV | [12 empty] | TBD | TBD | TBD | TBD | TBD | TBD
AES Kuihelani | Maui | PV + BESS | 60 MW/240 MWh |  | 69 KV | 11 |  | N/A | N/A | 3 |  | N/A |  | N/A | N/A | 0 | 1 | 9 | 0.51613 | 6 | TBD | TBD | TBD
Paeahu Solar LLC | Maui | PV + BESS | 15 MW/60 MWh |  | 69 KV | 11 |  | N/A | N/A | 3 |  | N/A |  | N/A | N/A | 0 | 1 | 6 | 2.6774 | See Note 10
Pulehu Solar | Maui | PV + BESS | 40MW/160MWh |  | 69 KV | 1 | 5 | 1 | 3 | 6 |  | 2 |  | See note 7
Kahana Solar | Maui | PV + BESS | 20MW/80MWh |  | 69 KV | 2 | 3 | 1 | 3 | 8 |  | 2 |  | 2 | 1 | 0 | 1 | 0 | 1 | See note 8
Kamaole Solar | Maui | PV+BESS | 40MW/160MWh |  | 69 KV | 1 | 3 | 1 | 12 | 3 |  | 2 |  | 1 | See note 9 | 0
AES Waikoloa Solar, LLC | Hawaii | PV + BESS | 30 MW/120 MWh | 2023-04-21 | 69 KV | 8 |  | N/A | N/A | 4 |  | N/A |  | N/A | N/A | 0 | 0 | 4 | 0.67742 | 5.0645 | 21 | 45 | 53 | 52
Hale Kuawehi Solar LLC | Hawaii | PV + BESS | 30 MW/120 MWh |  | 69 KV | 9 |  | N/A | N/A | 4 |  | N/A |  | N/A | N/A | 0 | 1 | 4 | 0.90323 | 4.9355 | TBD | TBD | TBD
NOTE: For projects prior to the time of Stage 2 RFPs, the Company did not track duration of intermediate steps.
1The Interconnection Requirements Study ("IRS") includes both the System Impact Study ("SIS") and Facility Study ("FS") components.
2Step 4a covers negotiation of the IRS Amendment between the Company and Developer so it is not possible to accurately attribute time to one party or the other.
3Total time in Column W is not the sum of Steps 1-7 as Steps 1 and 1a, and Steps 2 and 2a happen in parallel.
4Model requirements are provided in the specific RFP.
5 Null and void as of Dec 6, 2021.
6 Null and void as of May 4, 2022.
7 Null and void as of May 4, 2022.
8 Null and void as of Dec 23, 2022.
9 Null and void as of Mar 13, 2023.
10 Null and void as of Nov 17, 2023.

## #10e Interconnection Cost Overr
Interconnection Cost Overrun Reported Metric
Year | # of PPAs Completed | “# of PPAs’ Company-Owned Interconnection Facilities Actual Costs Over Estimate | % of Times Over Estimate
2017 | 2 | 0 | 0%
2018 | 2 | 2 | 100%
2019 | 3 | 0 | 0%
2020 | 4 | 1 | 25%
2021 | 0 | N/A | N/A
2022 | 1 | 0 | 0%
2023 | 2 | 1 | 50%